## Slide 1
2016 IT Roadmap Minnesota Eligibility Technology System
Feb. 2, 2016
Notices* * Post-Spring, Notices work will be handled by individual project teams
Renewals Functionality
Unique Person ID / ID Matching
METS-MMIS Interface Functionality
PRISM Iteration 2 Error Handling
Caseworker Functionality – Missing Task Functionality
MinnesotaCare Invoicing
Spring Release
Case Worker / County Improvements & Eligibility Integrity
Data Exchange - Carriers & IRS: 1095-A; 1095-A Automation; 1095 SHOP; 1095 Monthly; 1095 Plus (CMS); 834 ESI Open Enrollment Production Testing, True-up; ESOR GUI Phase 2 – Manual Enrollments
1095-B Phase 2
Reporting
METS Data Fixes
Security Enhancements: Compliance & Audits
Security Enhancements: Multi-Factor Authentication enhancements
Active Projects
Summer Release
Notices*
Renewal Functionality – QHP and Public Programs Batches
Unique Person ID / ID Matching
MNsure MMIS Interface Functionality
PRISM Iteration 3
Effective Dates
Periodic Data Match
Data Exchange - Carriers & IRS: 834 Effectuation; ESOR GUI Phase 3
2016 Business Focus Areas
Privacy & Security
Carrier Integration
Systems Development
Notices*
2017 QHP Marketplace Set-up
Eligibility System Upgrade (IBM/Curam)
Effective Dates
MNsure MMIS Interface Functionality
Fall Release
Winter Release
Projected to Execute
Projected to Execute
Project Selection Under Consideration
Data Exchange - Carriers & IRS
Reporting
METS Data Fixes
Maintenance & Operations team performs limited work on defect fixes.
Reporting

## Slide 2
2015 Release Plan
Project Status – FINAL
Work Currently Underway
Work in Planning Phase
Work Scheduled for Scoping/Planning
Open Enrollment Nov. 1-Jan 31
Work Completed
March
Sept.
Dec.
May
April
Feb 2, 2016
June
July
Aug.
Work Incomplete
Federal Hub Service Upgrade (VLP)
Public Programs Renewal Functionality
System Defect Fixes
Enrollment System of Record Fixes
Finance System Fixes
Cost-Effective determination logic change
Case generation functionality fix-Product Development Case
Enrollment data to carriers Phase 1 Previously scheduled for May
Streamlined Life Events - “Add Coverage”
Caseworker functionality simplification Phase 1 (task management)
Enrollment data to carriers Phase 2
Enhanced MA and BHP Renewal Functionality Phase 1
Eligibility Software Product Upgrade (IBM 6.0.5.7)
System Defect Fixes
Streamlined Life Events - “Add Coverage” - “Add Household Member” - “Remove Household Member”
Caseworker functionality simplification Phase 2 (task management/UI simplification)
Enrollment data to carriers Phases 2 & 3
Enhanced MA and BHP Renewal Functionality Phase 2
Usability Enhancements Phase 1
Safe at Home
System Defect Fixes
Security Enhancement: Multi-Factor Authentication – Pilot Phase 1
BHP Premium Rate Increase
MNsure MMIS Interface Functionality Package
QHP Renewals and Open Enrollment (#1)
2016 Shopping Readiness – Carrier Preview (#82)
Security Enhancement: Multi-Factor Authentication – Pilot Phase 2 (#3)
Enrollment data to carriers – 834 (#98)
Usability Enhancements Phase 2 (#14)
Reporting Functionality Phase 1 (#15)
MNsure MMIS Interface Functionality (#17)
Assister Portal Phase 1 (#21)
Infrastructure Improvements Phase 1 (#22)
System Defect Fixes
PRISM Interface - New Functionality Phase 1 and 2 (#55)
Reporting Functionality Phase 2 (#15)
True Up, 834 EDI production, 1095 electronic files, ESOR GUI (#98)
Renewals (#63)
MinnesotaCare Invoice & Payment Tracking Phase 1 (#61)
Security Enhancement: Multi-Factor Authentication (#62)
Citizen/Worker Portal Integration Phase 1 (#4)
Infrastructure Improvements Phase 2 (#22)
Notices – Limited Denial (#86)
Assister Portal Phase 2 (#58)
Usability Enhancements Phase 3 (#57)
Caseworker Functionality simplification (task management) (#81)
IRS 1095B (#66)
MNsure MMIS Interface Functionality (#17)
Change Wizards – defect fixes (#93)
= Change in Status
= Change in Scope
= Change in Timing
= Project Addition
S
Oct.
Summer Release
Fall Release
Winter Release
(#) Numbers in parentheses indicate MNsure IT Project number; numbers may change as project phases progress.