## Slide 1: Budget Process Overview
Britta Reitan
State Budget Director
October 2019

## Slide 2: Biennial Budget Process -Executive Branch-
Date | Budget Development Activities
April – June | Development of budget document form and format and consultation with legislators and staff
June - September | Early June: Agency/Program/Activity instructions issued July: Agency budget structure changes proposed and considered (inc. consultation with legislative staff and EBO) August: Preparing fiscal information (base budget) instructions available, including internal service and federal funds August: Budget narratives due from agencies August: Budget proposal (change) instructions available September: Departmental Earnings instructions available August – October: Base budget reconciliation work in BPAS (Agencies/EBOs)
October | October 1: Agency Budget background narratives completed; posted to website October 15: Base/enacted budget information due in BPAS October 15: Agency change item requests due to MMB including evidenced based proposals (considered non-public, preliminary budget info) Non-Executive Branch budget requests due to MMB

## Slide 3: Biennial Budget Process -Executive Branch- cont’d
Date | Budget Development Activities
November | Analysis of agency options by EBOs Review and reconciliation of base budget information in BPAS Analysis of evidence based proposals by MMB results team and EBOs Preparation of November forecast by economic analysis and budget division Base budgets published and sent to legislature (November 30th)
December | November forecast released Repricing of original agency requests to new base forecast (November) Revised change instructions issued (as needed depending on November forecast) Governor’s budget development
January | Governor’s budget development Governor’s Budget Recommendation release (fourth Tuesday; if new Governor, third Tuesday in February)
February | Preparation of February forecast by economic analysis and budget division Forecast adjustments made in BPAS for revenue and forecast spending February forecast Released
March | Repricing Governor’s Original Rec. to February forecast base Governor’s Revised Budget development Release of Governor’s Revised Budget

## Slide 4: Governor’s Budget Document
With the Governor’s budget release, MMB produces a comprehensive budget document including narrative and financial tables containing base and change item funding and spending information for all state funds and agencies.
The FY 2020-21 Governor’s Budget document was 4,027 pages and contained complete budget information for 105 agencies, boards, and commissions and 134 state funds.
Each agency’s budget book contains an agency profile narrative and larger agencies include program and activity narrative information. Financial tables include
  Sources of funds
  Uses of funds
  Summary of changes from base
Change item pages are also included for each change recommended by the Governor.